## Slide 1
CIST 1422 · GAME DESIGN DOCUMENT AND PROJECT PLAN
Building a Project Plan in GitHub, by Hand
A step-by-step walkthrough of the Lantern Keeper example: repo, labels, milestones, issues, and a GitHub Project with Board, Roadmap, and Table views.
The example board was generated by a script. Today we build the same thing by clicking through GitHub ourselves.
Notes: Open the example repo's Projects tab in another browser tab so you can switch between the slides and the real board. The PowerShell script in the repo (setup-example-project.ps1) automates everything on these slides. Students should do it by hand at least once so they understand each part.

## Slide 2
THE BIG PICTURE
The finished plan: five parts
CIST 1422 · Lantern Keeper example plan
Repository
Holds the README with a one-paragraph GDD summary and the game's code later on.
Labels
8 areas of work: gameplay, ui, art, audio, tech, testing, docs, risk.
Milestones
5 dated checkpoints, from Plan Approved to Final Build.
Issues
26 tasks. Each has a description, acceptance criteria, a label, and a milestone.
Project
A board linked to the repo, with Scope, Estimate, and Target date fields and 3 views.
Repo → Labels → Milestones → Issues → Project → Views
Why this order? Labels and milestones must exist before you create issues, so you can tag each issue as you write it. The Project comes last because it shows issues that already exist.
Notes: Walk through each part and point to it in the live example. The repo holds labels, milestones, and issues. The Project is a separate object, linked to the repo, that adds custom fields and views on top of those issues.

## Slide 3
BEFORE YOU CLICK ANYTHING
Start with the GDD, not the board
CIST 1422 · Lantern Keeper example plan
Lantern Keeper (2D, top-down, Unity, Windows)
You're a lighthouse keeper during a storm. Lamps along the coast burn through their oil. Keep them lit until dawn, or passing ships wreck on the rocks.
Core loop: find the lowest lamp → run to it → refuel → watch for ships → repeat
Controls: WASD move, E refuel, Esc pause
Lose: 3 wrecks. Win: survive until dawn
Scope tier | What's in it
Must have | Movement, draining lamps, refueling, ships that wreck, lives and dawn timer, HUD, menus, Windows build
Should have | Oil barrel pickups, storms that ramp up difficulty, real pixel art, sound effects
Nice to have | Music and volume settings, sprint ability, trailer
Rule of thumb Every Must-have feature in the GDD becomes at least one issue. When time runs short, cut Nice to have first, then Should have. The Must-have tier by itself should still be a complete, playable game.
Notes: The board is a plan for building the game described in the GDD. If the GDD is vague, the tasks will be vague too. Point out that the Must-have tier by itself is a complete, playable game. That's the test for a good Must-have list.

## Slide 4
STEP 1
Create the repository
CIST 1422 · Lantern Keeper example plan
Click path: github.com › + › New repository
1
Name it after your game, for example lantern-keeper
2
Choose Public or Private (Private: invite your instructor)
3
Check Add a README file
4
Set Add .gitignore to the Unity template
5
Click Create repository
6
Edit the README: paste in your one-paragraph GDD summary, scope tiers, and milestones
Why the Unity .gitignore? Unity generates Library/, Temp/, and Logs/ folders that are huge and rebuilt automatically. The template keeps them out of Git so your repo stays small and clones fast.
Teams One person creates the repo, then goes to Settings › Collaborators and invites everyone else.
Notes: Demo this live. Point out the .gitignore dropdown. If students skip the Unity template, they will try to commit the Library folder (gigabytes) and pushes will fail or take forever.

## Slide 5
STEP 2
Create labels for each area of work
CIST 1422 · Lantern Keeper example plan
Click path: Repo › Issues › Labels › New label
Label | Description | Color
gameplay | Mechanics and game logic | #1D76DB
ui | Menus, HUD, screens | #5319E7
art | Sprites, tiles, animation | #E99695
audio | Music and sound effects | #F9D0C4
tech | Project setup, builds, tooling | #0E8A16
testing | Playtesting and bug fixing | #FBCA04
docs | GDD, plan, presentation | #C5DEF5
risk | Something that could derail the schedule | #B60205
Default labels GitHub starts every repo with labels like bug and enhancement. Keep bug, and delete any you won't use so the list stays clean.
One label per issue If a task needs two labels, it's probably two tasks.
Notes: Labels answer the question 'what kind of work is this?' Keep the list short. Eight is plenty. The colors are only for scanning the board quickly. The 'risk' label is red on purpose so risks stand out.

## Slide 6
STEP 3
Create dated milestones
CIST 1422 · Lantern Keeper example plan
Click path: Repo › Issues › Milestones › New milestone
Milestone | Due date | Done when…
Plan Approved | Tue Oct 27 | GDD and board submitted and approved
Prototype | Tue Nov 10 | Core loop is playable with grey boxes
Alpha | Tue Nov 24 | Every Must-have feature is in
Beta | Tue Dec 1 | Content complete, playtested, bug fixing
Final Build | Tue Dec 8 | Windows build, presentation, credits
For each one, fill in Title, Due date, and Description (paste the "Done when…" text).
Line them up with class Use your course calendar's due dates. Then the milestones match the dates you're actually graded on.
Free progress bar The Milestones page shows % complete based on how many of its issues are closed.
Notes: A milestone is a checkpoint with a date and a clear definition of done. GitHub shows a progress bar for each milestone based on closed issues, so students can see right away if they're behind.

## Slide 7
STEP 4 · PLANNING ON PAPER FIRST
Break the GDD into tasks
CIST 1422 · Lantern Keeper example plan
A good task is…
1
Small: one person, about 4 hours or less
2
Specific: you can tell when it's finished
3
Estimated: write down a guess in hours
4
Tiered: Must, Should, or Nice to have
5
Placed: belongs to exactly one milestone
The test If you can't write acceptance criteria for a task, it isn't specific enough yet. Split it or rewrite it.
Example: one GDD feature becomes four issues
"Keep the lamps lit"
Lamps with fuel that drains over time
gameplay · 3 h
Refuel a lamp with the E key
gameplay · 2 h
Ships wreck at dark lamps and cost a life
gameplay · 3 h
HUD: lives, dawn timer, and lamp fuel bars
ui · 3 h
Notes: Do this on paper or in a spreadsheet before creating issues. Use the lamp feature as a live example: ask students to suggest the pieces, then compare with the board. Note the inconsistency they may notice: the README says split anything over about 4 hours, and the pixel art task is 6. Ask whether they would split it (tiles vs. character sprites).

## Slide 8
STEP 5 · WRITING ISSUES
Anatomy of a good issue
CIST 1422 · Lantern Keeper example plan
Lamps with fuel that drains over time #5
Description
A Lamp prefab holds a fuel value from 0 to 100 that drains each second. At 0 the light turns off.
Acceptance criteria
☐ Drain rate is adjustable in the Inspector
☐ Light visibly dims as fuel drops
☐ Lamp reports when it goes dark
Scope: Must have | Estimate: 3 hrs | Milestone: Prototype
Labels gameplay Milestone Prototype Assignee you
Title
Says what will exist when it's done. Not "Lamps" or "Work on lamps."
Description
One or two sentences on what to build and how it should behave.
Acceptance criteria
A checklist you can test. This is your definition of "done."
Sidebar
Exactly one label, one milestone, and an assignee.
Notes: This is the exact format every issue in the example uses. The acceptance criteria are a checklist. GitHub renders '- [ ]' as checkboxes that you tick off as you work, and the issue list shows progress like '1 of 3'.

## Slide 9
STEP 5 · CREATING ISSUES
Create one issue per task
CIST 1422 · Lantern Keeper example plan
Click path: Repo › Issues › New issue
1
Type a specific title
2
Paste the body template and fill it in
3
Sidebar: pick one Label
4
Sidebar: pick the Milestone
5
Sidebar: assign a teammate
6
Click Create. Repeat for every task (26 in the example)
Body template (Markdown)
## Description
What to build, in one or two sentences.
## Acceptance criteria
- [ ] Something you can test
- [ ] Another thing you can test
**Scope:** Must have | **Estimate:** 3 hrs
**Milestone:** Prototype
Shortcut Write "- [ ]" and GitHub turns it into a checkbox you can tick.
Notes: Show how to paste the template. Suggest students keep the template in a text file and copy it for every issue. Optional, more advanced: put an issue template in .github/ISSUE_TEMPLATE so GitHub pre-fills the body.

## Slide 10
CHECK YOUR ESTIMATES
The example plan, by the numbers
CIST 1422 · Lantern Keeper example plan
Milestone | Due | Tasks | Must hrs | Should hrs | Nice hrs | Total hrs
Plan Approved | Oct 27 | 3 | 7 | 0 | 0 | 7
Prototype | Nov 10 | 7 | 18 | 0 | 0 | 18
Alpha | Nov 24 | 7 | 8 | 13 | 0 | 21
Beta | Dec 1 | 5 | 6 | 3 | 5 | 14
Final Build | Dec 8 | 4 | 5 | 0 | 2 | 7
Total |  | 26 | 44 | 16 | 7 | 67
44 hrs is the real plan
That's the Must-have work. The rest is a bonus if time allows.
Front-load the core
Prototype has the most Must-have hours. Get the core loop working early.
Cut from the bottom
If Alpha slips, the 7 Nice-to-have hours go first.
Notes: Add up your hours before you submit. Compare the total to the hours you actually have. This example has 67 hours of work, and 44 of them are Must-have. If a team's Must-have total doesn't fit the schedule, the plan isn't realistic yet. The table view's field sum does this math for you.

## Slide 11
STEP 6
Create the GitHub Project and link it
CIST 1422 · Lantern Keeper example plan
Click path: Your profile › Projects › New project
1
Pick the Board template
2
Name it, for example "Lantern Keeper - Project Plan"
3
Open ⋯ › Settings: add a short description
4
Link it: in the repo's Projects tab, click Link a project
5
Under Manage access, add teammates as Write and your instructor
6
Set Visibility to Public, or make sure your instructor has access
Project ≠ repo A Project is a view on top of your issues. It's owned by your account, not the repo, so you have to link it to the repo yourself.
Status is built in The Board template already has a Status field with Todo, In Progress, and Done.
Notes: Projects belong to a user or organization, not to a repo, which is why we link them. Once linked, the project appears under the repo's Projects tab. Teams: create it under the account that owns the repo and add teammates under Manage access.

## Slide 12
STEP 7
Add custom fields
CIST 1422 · Lantern Keeper example plan
Click path: Project › ⋯ › Settings › Custom fields › + New field
Field | Type | Options / format | What it's for
Status | Single select (built in) | Todo · In Progress · Done | Where the task is right now
Scope | Single select | Must have · Should have · Nice to have | What gets cut first
Estimate (hrs) | Number | e.g. 3 | Totals per milestone and scope
Target date | Date | Use the milestone's due date | Places the card on the Roadmap
Shortcut In Table view, click + at the end of the header row to add a field without opening Settings.
Milestone is already there Milestone, Labels, and Assignees come from the issues, so you don't need to add them.
Notes: Custom fields only exist in the Project. They don't show up on the issue page in the repo, which is why the example also writes Scope and Estimate into the issue body. The fastest way to add a field is the + at the right end of the Table view header row.

## Slide 13
STEP 8
Add the issues and fill in the fields
CIST 1422 · Lantern Keeper example plan
1
In the project, click + Add item at the bottom of a column
2
Type #, pick your repo, and select the issues to add
3
Switch to Table view. It's the fastest way to edit many cards
4
Fill in Scope, Estimate (hrs), and Target date for each row
5
Set Status: finished work → Done, current work → In Progress
6
Close the issues for finished tasks (GDD, board, repo setup)
Title | Status | Scope | Est
Write the GDD | Done | Must | 4
Player movement | In Progress | Must | 3
Refuel with E | Todo | Must | 2
Oil barrel pickups | Todo | Should | 2
Sprint ability | Todo | Nice | 3
Faster: from the issue On an issue's sidebar, use Projects to add it to the board while you're creating it.
Notes: Demo the # trick: typing # in the Add item box lets you search the linked repo's issues. Then switch to Table view and fill fields down the column. You can copy a cell and paste it into several selected cells. Close the issues for work that's already done, like the GDD.

## Slide 14
STEP 9
Set up three views
CIST 1422 · Lantern Keeper example plan
Board
Todo
In Progress
Done
Layout: Board
Columns: Status
Day-to-day work. Drag cards from Todo to Done.
Roadmap
Layout: Roadmap
Dates: Target date
Group by: Milestone
Shows the schedule. Are tasks piling up before one deadline?
Table
▸ Must have Σ 44 hrs
▸ Should have Σ 16 hrs
▸ Nice to have Σ 7 hrs
Layout: Table
Group by: Scope
Field sum: Estimate (hrs)
Shows the hours. Does the Must-have total fit your time?
Notes: The GitHub API can't create views, so even the script leaves this step to you. It takes about a minute. Rename the default view to Board. Click New view for the other two. Remember to click Save after changing a view's settings, or the changes stay local to you.

## Slide 15
PLANNING FOR PROBLEMS
Track risks as issues
CIST 1422 · Lantern Keeper example plan
Label a risk issue risk. Give it a fallback plan and a date to decide by.
RISK: Ship movement may take longer than planned
Why it's risky: Steering ships around rocks could be harder than estimated.
Fallback: Ships follow fixed paths instead.
Acceptance criteria: the decision is recorded in a comment. Decide by Nov 3 (Prototype)
RISK: Pixel art may not be finished in time
Why it's risky: Hand-made art is slow.
Fallback: Keep the greybox and use a credited free asset pack.
Acceptance criteria: the decision is recorded in a comment. Decide by Nov 17 (Alpha)
Why make risks issues? They stay on the board with a deadline instead of being forgotten in a document.
Notes: A risk isn't a task to build something. It's a decision you'll have to make by a certain date. Making it an issue keeps it on the board and gives it a deadline. Ask students: what's the riskiest feature in your GDD, and what's the fallback?

## Slide 16
AFTER THE PLAN IS APPROVED
Keep the plan up to date as you work
CIST 1422 · Lantern Keeper example plan
Move cards
Start a task: drag it to In Progress. Finish it: tick the acceptance criteria and move it to Done.
Close issues from commits
Put Closes #12 in a commit message. When it reaches the default branch, #12 closes and its card moves to Done.
Log new work
Every problem found in playtesting becomes a new issue labeled testing.
Re-estimate
If a task takes twice as long as you guessed, update the estimate. That's useful data for next time.
Cut on purpose
Running behind? Move Nice-to-have issues out of the milestone instead of quietly skipping them.
Compare at the end
Your final presentation shows the final board next to the original plan.
Notes: A plan that never changes is a plan nobody is using. Demo 'Closes #12': make a commit with that text, push it, and watch the issue close and the card move to Done (the project's built-in workflows do this by default).

## Slide 17
SELF-CHECK
Before you submit: checklist
CIST 1422 · Lantern Keeper example plan
Repo uses the Unity .gitignore
README has the GDD summary, scope tiers, and milestones
Labels for each area of work, including risk
4–5 milestones, each with a due date
Every Must-have feature has at least one issue
Every issue has acceptance criteria, a label, and a milestone
No task over about 4–6 hours
Project is linked to the repo
Scope, Estimate (hrs), and Target date are filled in
Board, Roadmap, and Table views are saved
Teammates assigned to issues (teams)
Instructor can see the project, plus a screenshot of the Board view
Notes: Have students go through this list on their own board before submitting. It lines up with what you'll look for when grading.

## Slide 18
YOUR TURN
Practice with your own GDD
1
Pick one Must-have feature from your GDD. Split it into 3–5 issues, each with acceptance criteria.
2
Estimate each one in hours. Is any over 4 hours? Split it.
3
What's the riskiest part of your game? Write it as a risk issue with a fallback and a decision date.
4
If Alpha slipped a week, which issues would you cut first?
Reference: the example repo's README, under "Make your own board in 10 minutes"
Notes: Give students 10–15 minutes to do questions 1–3 on paper, then have a few share. Then they can start creating real issues in their own repo.