## Slide 1: Planning Your Game
Game Design Document and Project Plan
Final Game Project · CIST 1422
Notes: Today we're kicking off the Final Game Project with its first deliverable: a Game Design Document and a Project Plan. The GDD says what the game is. The plan says how you'll actually get it built before the end of the semester.

## Slide 2: Why plan before you build
Scope creep
Ideas grow faster than the semester. A plan forces you to decide what's in and what's out.
Missed deadlines
Small tasks with estimates show you early when you're falling behind.
Team confusion
Everyone can see who owns what, and nobody builds the same thing twice.
The goal
A plan you can cut from.
If only your Must-have features get finished, you should still have a complete, playable game. Everything else is a bonus.
Notes: Every student game project runs out of time. The difference between a finished game and an unfinished one is usually not skill, it's scope. The plan is how you protect yourself.

## Slide 3: The assignment has two parts
Part 1 · Game Design Document
At least 500 words
Built on MDA, the Elemental Tetrad, or another framework
Detailed enough that someone else could start building it
Part 2 · Project Plan
Scope tiers, tasks, and time estimates
Dated milestones, roles, and risks
Tracked on a real board you'll keep using
Submit: GDD + Project Plan + link to your board + a screenshot of it · 250 points · Due date on Canvas
Notes: Part 1 is the what. Part 2 is the how and when. The board you build for Part 2 isn't busywork: you'll update it all the way to the final build, and we'll look at it at each milestone check-in.

## Slide 4: Part 1: The Game Design Document
Define your game down to the level of implementation
Notes: Example GDDs to browse: gamedocs.org/documents. Look at how much detail real teams write before building anything.

## Slide 5: Pick a design framework
MDA
Mechanics
Rules and inputs
Dynamics
What happens in play
Aesthetics
What the player feels
Designers build from Mechanics outward. Players experience the game from Aesthetics inward. Start by naming the feeling you want, then pick mechanics that create it.
Lantern Keeper: refueling lamps under a timer (M) → frantic route planning (D) → challenge (A)
Elemental Tetrad
Aesthetics
Look, sound, feel
Mechanics
Rules and goals
Story
Events and world
Technology
Engine and platform
Schell's four elements. Aesthetics is most visible to the player, Technology least. All four must support each other.
Notes: Either framework is fine, or another one you can justify. MDA is great for mechanics-heavy games. The Tetrad works well if story and technology matter to your idea. Whichever you choose, actually use it to structure your analysis.

## Slide 6: What your GDD must cover
Concept and pitch
Elevator pitch, genre, target player, "X meets Y"
Framework analysis
Walk through MDA or the Tetrad for your game
Core loop
What the player does moment to moment, and why
Controls
Every input on your platform and what it does
Look and feel
Art style, palette, camera, HUD, audio, mood board
World and content
Levels, characters, enemies, items, story
Win, lose, progress
How a session starts and ends, and difficulty curve
Technical scope
Engine version, platform, packages, credited assets
Notes: These eight sections are the minimum. Visuals count: a sketch of the core loop, a mood board, or a level layout often says more than a paragraph.

## Slide 7: Part 2: The Project Plan
Turn your design into work you can finish by the deadline
Notes: Every example in this section comes from a sample game called Lantern Keeper, a 2D top-down game where you keep coastal lamps lit so ships don't wreck. Its full plan lives on a real GitHub board you can browse.

## Slide 8: Sort every feature into scope tiers
Must have
The minimum playable game
Movement and refueling
Lamps that drain fuel
Ships that wreck at dark lamps
Lives, dawn timer, HUD, menus
Windows build
Should have
Makes it good
Oil barrel pickups
Storms that ramp difficulty
Real pixel art
Sound effects
Nice to have
Only if there's time
Music and volume slider
Sprint ability
Gameplay trailer
Running out of time? Cut from the right first.
Notes: Be honest here. If your Must-have column is twenty features long, it isn't a Must-have list. Ask: if I shipped only this column, would it be a whole game?

## Slide 9: Break features into tasks you can finish
Too vague
"Make the ships"
No size, no finish line
Specific and sized
"Ships spawn and sail past the coast"
Estimate: 4 hrs · Milestone: Prototype
Rule of thumb: if a task is over 4 to 6 hours, split it.
Acceptance criteria
A checklist that defines "done" for a task:
Ships spawn off-screen on a timer
Spawn interval is adjustable in the Inspector
Ships are destroyed after leaving the screen
Can't write criteria? The task isn't clear yet.
Notes: Estimates will be wrong, and that's fine. The point is to notice early. Acceptance criteria keep you from polishing one feature forever: when the boxes are checked, move on.

## Slide 10: Set milestones with dates
Oct 27
Plan Approved
GDD and board approved
Nov 10
Prototype
Core loop playable with grey boxes
Nov 24
Alpha
Every Must-have feature is in
Dec 1
Beta
Content complete, playtested
Dec 8
Final Build
Build, presentation, credits
Each milestone needs a date and a "done when" test. Example dates are from the Lantern Keeper plan. Use our course calendar for yours.
Notes: At least four milestones from now to the end of the semester. A milestone is a checkpoint you can demonstrate, not just a date on the calendar.

## Slide 11: Name your risks and roles early
Ship movement may take longer than planned
Fallback: ships follow fixed paths. Decide by Nov 3.
Pixel art may not be finished in time
Fallback: keep the greybox and use a credited free asset pack.
Midterms and Thanksgiving week
Plan: finish Must-have tasks before Nov 20; cut Should-haves first.
List two or three things that could go wrong, and what you'll do if they do.
Team projects
Every task has one owner
Split by area: gameplay, art, UI, audio
Balance the hours, not the task count
Example: Maya codes (37 hrs), Jordan does art and UI (31 hrs)
Notes: In the example, risks are tracked as issues with a red risk label so they stay visible on the board instead of being forgotten in a document.

## Slide 12: Putting your plan on a board
The recommended tool: GitHub Projects
Notes: You can use another tool if you prefer, and we'll list free options at the end, but GitHub Projects is what I recommend because your code and your plan live in the same place.

## Slide 13: Why GitHub Projects
Code and plan in one place
Your Unity repo, issues, and board live side by side.
Commits close tasks
Mention an issue in a commit and its card moves to Done.
Progress you can show
The board's history is evidence of your work at each milestone.
Free
Included with any GitHub account. No trial, no limits that matter here.
Try it
git commit -m "Add lamp refueling.
Closes #6"
Issue #6 closes and its card moves to Done when you push.
Notes: Keywords that work: Closes, Fixes, or Resolves followed by the issue number. It happens when the commit reaches the default branch.

## Slide 14: What the example board looks like
Todo 23
Refuel a lamp with the E key
gameplay
2h
Ships spawn and sail past the coast
gameplay
4h
Greybox the coastline level
art
2h
+ 20 more cards
In Progress 2
Player movement (WASD, top-down)
gameplay
3h
Lamps with fuel that drains over time
gameplay
3h
Done 3
Write the Game Design Document
docs
4h
Build the project board
docs
2h
Set up Unity project and Git repo
tech
1h
Notes: This is a simplified picture of the Lantern Keeper board. Browse the real one at github.com/jcallinan/CIST1422-Example-Project-Plan, under the Projects tab. Notice the realistic mix: some Done, some In Progress, most still Todo.

## Slide 15: Anatomy of a task
Ships spawn and sail past the coast #7
Description
Ships spawn off-screen on a timer and travel along the coast past each lamp.
Acceptance criteria
Spawn interval is adjustable
Ships destroyed after leaving the screen
gameplay
Milestone: Prototype
Status | Todo → In Progress → Done
Scope | Must / Should / Nice to have
Estimate (hrs) | Your best guess. Split anything over ~4
Milestone | Which checkpoint it belongs to
Target date | Drives the Roadmap timeline view
Owner | Teams: the one person responsible
Labels | Area: gameplay, ui, art, audio, risk…
Scope, Estimate, Target date, and Owner are custom fields you add once.
Notes: Status comes built in. Scope, Estimate, and Target date are custom fields you add once. Milestones are created in the repo under Issues, then Milestones.

## Slide 16: Set up your board in 10 minutes
1
Create a repo for your game with the Unity .gitignore
2
Profile → Projects → New project → Board template
3
Project settings: link it to your repo
4
Add fields: Scope, Estimate, Target date, Owner
5
Repo → Issues → Milestones: add dated milestones
6
One issue per task: label, milestone, criteria
7
Add a Roadmap view and a Table view by Scope
8
Teams: add collaborators, assign every issue
9
Share the project and screenshot the Board view
Stuck? Copy the structure of the Lantern Keeper example.
Notes: New projects open in a table view. Switch the layout to Board for the kanban columns. The repo README for the example walks through these same steps.

## Slide 17: Prefer another tool? These are free too
With your Pitt Microsoft 365
Microsoft Planner
Kanban board, due dates, checklists
Microsoft Loop
Shared pages; task lists sync to Planner
Lists and Excel
Structured trackers or a simple Gantt chart
Built for game developers
Codecks
Free for up to 5 users; free Pro for students
HacknPlan
Boards linked to a built-in GDD
General purpose
Trello
Free: 10 boards, 10 collaborators
Notion
Free Plus plan with your school email
Whatever you choose: submit a link your instructor can open, plus a screenshot.
Notes: Planner is available to every Pitt student through Microsoft 365; log in at microsoft365.com. Free tier details checked October 2026 and may change.

## Slide 18: How it's graded (250 points)
Chart: 
| Writing and 500-word minimum | Planning tool setup | Technical scope | Milestones, roles, risks | Look and feel | Scope tiers, tasks, estimates | Core loop, controls, gameplay detail | Concept, pitch, framework analysis
Points | 10 | 20 | 20 | 30 | 30 | 40 | 50 | 50
150
points for the GDD
100
points for the plan and board
Notes: The GDD categories add to 150 (concept and framework, gameplay, look and feel, technical scope, writing) and the plan categories add to 100.

## Slide 19: Your next steps
1. Pick a framework and draft your GDD
2. Sort features into scope tiers and break them into tasks
3. Build your board and submit the link + screenshot
Example: github.com/jcallinan/CIST1422-Example-Project-Plan
Notes: Questions? Remember the due date is on Canvas, and bring your board to each milestone check-in.